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1.0	Introduction
Environmental sanitation is among the powerful drivers of human development as it affects quality of life. It contributes to the improvement of health and also help to create wealth when people become healthy and productivity increases. Addressing poor human behaviour and attitude towards sanitation is critical to achieving any meaningful progress in any society.
It is in this regard that the Environmental Health and Sanitation Unit of the Eastern Regional Coordinating Council exist, to facilitate the improvement of environmental health and sanitation in the various Municipal/District Assemblies through regular monitoring, supportive supervision, evaluation and giving feedback to ensure clean, safe and healthy environment to help promote the health of the people in all communities.
The main objectives of the regional monitoring visit was to assess the progress and effectiveness of the work of Environmental Health Unit. The monitoring activity to the 33 MDAs was conducted by three (3) staff members including a driver from the unit from 2nd May, 2023 to 25th July, 2023. 
The report also summarizes the main findings and data collected within Municipalities/districts following the meetings we held with staff members.
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1. The monitoring team ascertain that, all other M/DEHOs did not have significantly enough sanitary tools for usage with exception of Kwahu West Municipality, a situation which was likely to affect planned/routine community clean up exercises.    The most hit MDAs with poor stock of sanitary tools and equipment included:
· Birim Central Municipal Assembly 
· Akyemansa District Assembly
· Birim South District Assembly
· Upper West Akim District Assembly
· Atiwa East District
· Kwahu East
2. On the issue of waste collection, majority of the MDAs visited made compliant of the poor state of their assigned Zoomlion communal metal containers. Notably among them were;
· Kwahu East
· New Juaben South
· Abuakwa south
· Lower Manya
· Kwaebibrem
3. The monitoring/inspection revealed that most of the MDAs have not regularized their operations with respect to scraps and electronic waste management activities. Scrap and waste collections were not formal. Even though there were some identified collection centers, those centers had not been registered by the MDA. Transportation of e-waste is still informal and workers were doing this work without any form of work place safety and protection. 
4. 76% of the districts have official notices that are served for the contraventions of appropriate sanitation legislations and abatement of nuisances.
5. Out of the 33 districts, only 30% showed evidence of available scribe book for scribing court cases and complaints. The report also revealed that only 66% of the districts had summon books used in prosecution activities whereas the remaining 34% did not show any evidence of their official summon books.
6. General sanitation conditions at slaughterhouses in the region is not encouraging and pose risk of disease outbreak. Among the districts/Municipals with poor slaughterhouse conditions are New Juaben South, Lower Manya Krobo, Afram Plains North, Achiase and Upper Manya Krobo.  
7. Lack of budgetary allocations to the unit in procuring motor bikes, offices computers with its accessories as well as procurement of sanitary tools/equipment to scale up all environmental health activities.
8. Overall, the Environmental Health and Sanitation unit in the region generated an of 958,232.47
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