REPUBLIC OF GHANA

# MINISTRY OF ROADS AND HIGHWAYS DEPARTMENT OF URBAN ROADS

## EASTERN REGIONAL OFFICE

THIRD QUARTER REPORT, 2023

### SEPTEMBER, 2023

Prepared by:

Regional Office

Department of Urban Roads – Eastern Region Koforidua

EXECUTIVE SUMMARY

This report presents details of the activities of the Eastern Regional Office of the Department of Urban Roads (DUR) for the 3rd Quarter of 2023. The report highlights activities on routine and approved "on-going" periodic maintenance contracts/projects, including finance and administration.

The main objective of the DUR is to improve travel in the urban areas of Ghana in a safe and efficient manner. The Regional Office's principal objective is the management of selected major/minor arterials and some distributor/collector roads in urban areas of the region. The tasks also include planning, implementation, and maintenance of traffic management systems that improve the capacity and efficiency of urban transportation, thereby promoting socio-economic growth and reducing poverty.

The region is responsible for the management of a total urban road network of 6,801.27, out of which 19% is paved and 81% unpaved, as presented in Figure 2. 1. The road network size and condition were updated in the third quarter of 2023. The overall condition mix of the network is 16% good, 4% fair, and 80% poor.

The Regional Office has received a cumulative amount ¢11,450,000.00 as 2023 budgetary allocation for routine maintenance works. During the period under review, the total certified amount for routine maintenance works was ¢ 452,281.90 for the Regional Office. These activities included grading, and office cleaning and auxiliary works. Procurement of works are ongoing in the various municipal Assemblies.

For periodic maintenance, as of September 2023, our project portfolio consisted of forty (40) projects: thirty-three (33) road rehabilitation and seven (7) asphalt overlay Works. As of the reporting period, 60% of project sites have been vacated, and contractors are demobilizing from the site as a result of disruption in cash flow. Only one (1) Contractor representing 2% carried out some works during the period under review and 18% of projects had been substantially completed.

Figure 1. 2: Eastern Regional Map with its respective MDAs

The region has a total population of 2,925,653 persons (1,436,951 males and 1,488,720 females) and a population growth rate of about 1.0%, according to the 2021 Population and Housing Census, Ghana Statistical Service. The urban-rural split is 51.5% against 48.5%. With the setting up of the Local Government Service by the Local Governance Act of 2016, Act 936, with Amendment Act 940, which completely decentralizes roads and transport functions to the Metropolitan/Municipal/District Assemblies (MMDAs), the Regional Offices were set up in 2014 to manage assigned major/minor and some collector/distributor road networks in urban areas in the regions. The offices also provide technical backstopping to the Metropolitan/Municipal/District Roads Departments (MMDRDs) to ensure capacity is developed within. The Regional Offices coordinate and monitor the activities of the

Network Distribution

Paved 19%

Unpaved 81%

Figure 2. 1: Proportion of Paved and Unpaved Network for Eastern Region

Table 2. 1: DUR Road Inventory in Eastern Region

|  |  |  | CONDITION |  |  |
| --- | --- | --- | --- | --- | --- |
| SURFACE TYPE |  | TOTAL NETWORK/KM | GOOD | FAIR | POOR |
| Paved |  | 1,284.56 | 1,077.15 | 273.38 | 64 |
| Unpaved (Gravel) | 2,739.29 | 5,516.70 | - | - | 5,516.70 |
| Unpaved (Earth) | 2,777.41 |  | - | - |  |
| Total |  | 6,801.256 | 1,077.15 | 273.38 | 5,450.70 |
|  |  | % | 16% | 4% | 80% |

The proportion of good roads within the existing 6,801.25km network is inadequate and does not meet the demand of the people, especially in farming communities and low-income areas, and in view of the high rate of urbanization in the region. Presently, most of the Municipalities' distributor/collector roads and junctions that offer medium levels of mobility and direct access into urban areas and other land uses have not been developed.

Below is the road inventory and condition mix for the region.

3rd Quarter Report, 2023	Department of Urban Roads – Eastern Region

Table 2. 2: DUR Road Inventory for the various MDAs

| MMA | TOTAL NETWORK LENGTH (KM) | SURFACE TYPE |  |  |  |  |  |  |  | CONDITION |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | PAVED |  | UNPAVED |  | GRAVEL |  | EARTH |  | GOOD |  | FAIR |  | POOR |  |
|  |  | KM | % | KM | % | KM | % | KM | % | KM | % | KM | % | KM | % |
| New Juaben South (Koforidua) | 372.4 | 111.13 | 30 | 261.27 | 70 | 169.83 | 65 | 91.44 | 35 | 86.18 | 23 | 25.54 | 7 | 260.68 | 70 |
| New Juaben North (Effiduase) | 323.9 | 72.92 | 23 | 250.98 | 77 | 100.39 | 40 | 150.59 | 60 | 38.87 | 12 | 35.63 | 11 | 249.40 | 77 |
| Akuapem North (Mamfe/Akropong) | 511.59 | 45.01 | 9 | 466.58 | 91 | 279.70 | 60 | 186.88 | 40 | 41.54 | 8 | 5.12 | 1 | 464.94 | 91 |
| Yilo Krobo (Somanya) | 496.12 | 95.39 | 19 | 400.74 | 81 | 140.26 | 35 | 260.48 | 65 | 69.46 | 14 | 24.81 | 5 | 401.86 | 81 |
| Lower Manya Krobo (Odumase) | 378.09 | 69.08 | 18 | 309 | 82 | 123.6 | 40 | 185.4 | 60 | 64.28 | 17 | 7.56 | 2 | 306.25 | 81 |
| Suhum | 426.97 | 21.49 | 5 | 405.48 | 95 | 182.46 | 45 | 223.01 | 55 | 21.35 | 5 | 21.35 | 5 | 384.27 | 90 |
| Nsawam Adoagyire | 633.81 | 143.26 | 23 | 490.55 | 77 | 245.28 | 50 | 245.28 | 50 | 57.04 | 9 | 19.01 | 3 | 557.75 | 88 |
| Birim Central (Akim Oda) | 215.5 | 28.23 | 13 | 187.27 | 87 | 112.36 | 60 | 74.91 | 40 | 23.71 | 11 | 4.31 | 2 | 187.49 | 87 |
| West Akyem (Asamankese) | 389.07 | 9.57 | 2 | 379.5 | 98 | 170.78 | 45 | 208.73 | 55 | 93.50 | 24 | 23.22 | 6 | 272.35 | 70 |
| Kwahu West (Nkawkaw) | 648.71 | 95.26 | 15 | 553.45 | 85 | 332.07 | 60 | 221.38 | 40 | 77.85 | 12 | 19.46 | 3 | 551.40 | 85 |
| Abuakwa South (Kyebi) | 312 | 91.78 | 29 | 220.22 | 71 | 132.13 | 60 | 88.09 | 40 | 78.00 | 25 | 12.48 | 4 | 221.52 | 71 |
| Abuakwa North (Kukurantumi) | 425.76 | 101.18 | 24 | 324.57 | 76 | 113.6 | 35 | 210.97 | 65 | 93.67 | 22 | 8.52 | 2 | 323.58 | 76 |
| Kwaebibrim (Kade) | 585.66 | 264.12 | 45 | 321.54 | 55 | 202.57 | 63 | 118.97 | 37 | 240.12 | 41 | 23.43 | 4 | 322.11 | 55 |
| Akuapim South (Aburi) | 474.88 | 61.6 | 13 | 413.28 | 87 | 247.97 | 60 | 165.31 | 40 | 52.24 | 11 | 9.50 | 2 | 413.15 | 87 |
| **Kwahu South (Mpraeso) | 606.8 | 74.54 | 12 | 532.26 | 88 | 186.29 | 35 | 345.97 | 65 | 66.75 | 11 | 6.07 | 1 | 533.98 | 88 |
|  | 6,801.26 | 1,284.56 | 19 | 5,516.69 | 81 | 2,739.29 | 50 | 2,777.41 | 50 | 1,077.15 | 15 | 273.38 | 4 | 5,580.70 | 81 |

3rd Quarter Report, 2023	Department of Urban Roads – Eastern Region

CHAPTER THREE – FINANCE AND ADMINISTRATION

  - Financial Overview

As of the end of the reporting period, the Regional Office received a total amount of ¢264,617.00 and an amount of GH¢167,986.84 catered for administrative expenses. Table 3. 1 highlights the financial status of the office for the period under review.

Table 3. 1: 2023 3rd Quarter Financial Status of Regional Office

| PERIOD | REVENUE (Gh¢) | EXPENDITURE (Gh¢) |
| --- | --- | --- |
| (July, 2023) | 244,617.00 | 72,780.84 |
| (August, 2023) | - | 63,283.00 |
| (September, 2023) | 20,000.00 | 31,923.42 |
| TOTAL | 264,617.00 | 167,986.84 |

  - Administration

    - Staff Strength/Organogram

The current permanent staff level of the regional office as of the end of the third quarter of 2023 was twenty (20). Established positions in the department are the Regional Director (Head of the Department), Maintenance Engineer, Traffic/Development Engineer and Ag. Regional Quantity Surveyor. Others include one (1) Senior Quantity Surveyor, three (3) Assistant Quantity Surveyors, One Assistant Engineer. Two (2) Technician Engineers, one (1) Assistant Geodetic Engineer, Accountant, Accounts Technician, Procurement Officer, two (2) Assistant Procurement Officers, Secretary, Executive Officer and Sanitary Laborer. Figure 3. 1 and Table 3. 2 below show the current organogram and staff list for the regional office, respectively.

Project Outline - Construction of Selected Roads in Asamankese (10.00km) – Lot 9

        - Project Outline (Lot 9)

| Contract Name | Construction of Selected Roads in Asamankese (10.00km) – Lot 9 |
| --- | --- |
| Contractor | Newcase Construction Limited |
| Municipality/District | West Akyem |
| Cumulative Physical Progress (Status) | 20 % |
| Financial Progress | 14% |
| Contract Sum | Gh¢16,660,000.00 |
| Revised Contract Sum | Gh¢16,660,000.00 |
| Certified Payments | Gh¢ 2,128,587.46 |
| Funding | Ghana Road Fund |
| Supervising Consultant | Eastern Regional DUR Office |
| Procurement Method | National Competitive Tendering |
| Contract Reference Number | DUR/ER/GRF/PM/CONST/2017/011 |
| Contract Award Date | 25th October, 2017 |
| Commencement Date | 22nd December, 2017 |
| Duration | 18 Months |
| Completion Date (As per Contract) | 21st June, 2018 |
| Time Elapsed to Date | 81 Months (450 %) |

Progress Photographs

Plate 2: After construction of 0.6m U-Drain

        - Scope of Works

The scope of works consists of the upgrading of 10.00km gravel road to bituminous surface. The detailed scope includes the following;

- Construction of 0.45m diameter Open U-Drain (0.55km)

- Construction of 0.6m diameter Open U-Drain (13.40km)

- Construction of 0.9m diameter Open U-Drain drains (0.67km)

- Construction of 1.2m diameter Outfall Drain (0.20km)

- Construction of 1.2m diameter Single Cell Pipe culvert (2 no.)

- Earthworks- Filling to Sub-grade with suitable natural gravel materials of 10.00km

- Pavement Works-Natural Gravel Sub-base & Base Course and Stabilized Base Course (150mm thick each) = 10.00km

- Surfacing Works-Primer Seal and Seal of 10.00km

        - Physical Progress

ABANDONED: Works Suspended and Contractor Demobilized from Site. 4.5km of 0.6m and 0.9m dia. concrete U-Drains constructed. Warning letters have been issued to the Contractor. Overall physical progress is 20%.

Outstanding Works: 10.80km of open drainage works and 10km of Subbase, base, primer seal and seal works.

      - Project Outline - Construction of Selected Roads in Kwabeng (10.00km) – Lot 10

        - Project Outline (Lot 10)

| Contract Name | Construction of Selected Roads in Kwabeng (10.00km) – Lot 10 |
| --- | --- |
| Contractor | Jilcon Limited |
| Municipality/District | Atiwa West |
| Cumulative Physical Progress (Status) | 55% |
| Financial Progress | 48% |
| Contract Sum | Gh¢17,500,000.00 |
| Revised Contract Sum | Gh¢ 18,872,990.00 |
| Certified Payments | Gh¢ 8,668,195.87 |
| Funding | Ghana Road Fund |
| Supervising Consultant | Eastern Regional DUR Office |
| Procurement Method | National Competitive Tendering |
| Contract Reference Number | DUR/ER/GRF/PM/CONST/2017/012 |
| Contract Award Date | 25th October, 2017 |
| Commencement Date | 22nd December, 2017 |
| Duration | 18 Months |
| Completion Date (As per Contract) | 21st June, 2019 |
| Duration (Revised) | 42 Months |
| Completion Date (Revised) | 31st May, 2021 |
| Time Elapsed to Date | 69 Months (164 %) |

        - Scope of Works

The scope of works consists of the upgrading of 7.20km gravel road to bituminous surface. The detailed scope includes the following;

- Construction of 0.45m diameter Open U-drain (0.30km)

- Construction of 0.6m diameter Open U-drain (9.24km)

- Construction of 0.9m diameter Open U-drain drains (2.45km)

- Construction of 1.2m diameter outfall drain (0.20km)

- Construction of 1.5 x 1.2m storm drain (0.20km)

- Construction of reinforced concrete retaining wall (0.30km)

- Construction of 0.9m diameter pipe culvert (2 no.)

- Construction of 1.2m diameter double cell pipe culvert (2 no.)

- Construction of 1.2m diameter single cell pipe culvert (4 no.)

- Construction of 2 x 2.5m single cell box culvert (1 no.)

- Earthworks- Scarification and excavation in cutting sections of existing unsuitable material, filling to Sub-grade with suitable natural gravel materials of 7.2km

- Pavement Works-Natural Gravel Sub-base and Base Course (150mm thick each), Primer Seal and Seal = 7.2km

        - Physical Progress

ABANDONED: Works suspended. 6.5km and 4.5km of Primer seal and seal completed respectively. Slow rate of progress.

        - Outstanding works

- 11.62km of Open U-drains

- 117m of Storm drain

- 2nr. 1.2m Pipe Culvert

- 1.46km of Kerb

- 300m of Reinforced Retaining Wall

- 3.79km of Subbase

- 2.84km of Stabilized Base

- 6.30km of Primer Seal

- 11.80km of Seal

- 15nr. Speed Humps

      - Project Outline - Rehabilitation of Selected Roads in New Juaben Municipality (10.00km) – Lot 12

        - Project Outline - Lot 12

| Contract Name | Rehabilitation of Selected Roads in New Juaben Municipality (10.00km) – Lot 12 |
| --- | --- |
| Contractor | Kasmo Company Limited |
| Municipality/District | New Juaben |
| Cumulative Physical Progress (Status) | 89% |
| Financial Progress | 75% |
| Contract Sum | Gh¢15,263,474.31 |
| Revised Contract Sum | Gh¢ 31,419,634.21 |
| Certified Payments | Gh¢ 22,084,450.58 |
| Funding | Ghana Road Fund |
| Supervising Consultant | Eastern Regional DUR Office |
| Procurement Method | National Competitive Tendering |
| Contract Reference Number | DUR/ER/GRF/PM/REH/2017/014 |
| Contract Award Date | 25th October, 2017 |
| Commencement Date | 22nd December, 2017 |
| Duration | 18 Months |
| Completion Date (As per Contract) | 21st June, 2019 |
| Completion Date (Revised) | 22nd December, 2021 |
| Time Elapsed to Date | 69 Months (144 %) |

        - Scope of Works

The scope of works consists of the upgrading of 7.8km gravel road to bituminous surface. The detailed scope includes the following;

          - Construction of 0.6m diameter Open U-drain (6.5km)

          - Construction of 0.9m diameter Open U-drain drains (0.5km)

          - Earthworks- Scarification and excavation in cutting sections of existing unsuitable material, filling to Sub-grade with suitable natural gravel materials of 7.8km

          - Pavement Works-Natural Gravel Sub-base and Base Course (150mm thick each) = 7.8km

          - Surfacing Works-Primer Seal and Seal of 7.8km

        - Scope of Works (Additional Works)

The scope of additional works consists of the upgrading of 12.70km gravel road to bituminous surface. The detailed scope includes the following;

          - Construction of 0.6m diameter Open U-drain (18.70km)

          - Construction of 0.9m diameter Open U-drain (1.00km)

          - Construction of Trapezoidal Drain (1.00km)

          - Construction of Storm drain (40m)

          - Construction of 0.9m diameter Pipe Culvert (1no.)

          - Construction of 1.2m diameter Pipe Culvert (10 no.)

          - Construction of Reinforced Concrete Retaining wall (0.50km)

          - Construction of Speed Humps (28 nr.)

- Physical Progress

SUSPENDED: Works suspended. Drainage and 5km of Primer seal works completed. Drainage and paving works suspended.

Outstanding works: open drainage works, 3nr. Pipe culverts, 14km of road paving and road furniture.

      - Project Outline - Rehabilitation of Selected Roads in Akim-Oda (10.00km) – Lot 15

        - Project Outline - Lot 15

| Contract Name | Rehabilitation of Selected Roads in Akim-Oda (10.00km) – Lot 15 |
| --- | --- |
| Contractor | Jo-Mint Associates Limited |
| Municipality/District | Birim Central |
| Cumulative Physical Progress (Status) | 55% |
| Financial Progress | 23% |
| Contract Sum | Gh¢11,061,172.93 |
| Revised Contract Sum | Gh¢11,061,172.93 |
| Certified Payments | Gh¢2,598,526.80 |
| Funding | Ghana Road Fund |
| Supervising Consultant | Eastern Regional DUR Office |
| Procurement Method | National Competitive Tendering |
| Contract Reference Number | DUR/ER/GRF/PM/REH/2017/017 |
| Contract Award Date | 25th October, 2017 |
| Commencement Date | 22nd December, 2017 |
| Duration | 18 Months |
| Duration (Revised) | 43 Months |
| Completion Date (As per Contract) | 21st June, 2019 |
| Completion Date (Revised) | 27th July, 2021 |
| Time Elapsed to Date | 69 Months (164%) |

        - Scope of Works

The scope of works consists of the upgrading of 10km gravel road to bituminous surface. The detailed scope includes the following;

- Construction of 0.6m diameter Open U-drain (8.10km)

- Construction of 0.9m diameter Open U-drain drains (1.26km)

- Construction of 0.9m diameter Outfall drain (0.10km)

- Construction of 1.2m diameter Outfall drain (0.10km)

- Reinforced concrete wall (0.10km)

- Construction of 0.9m Single Cell Pipe Culvert (1no.)

- Construction of 0.9m Double Cell Pipe Culvert (1no.)

- Construction of 1.2m Double Cell Pipe Culvert (1no.)

- Construction of 1.2m Single Cell Pipe Culvert (1no.)

- Construction of 2 x 3m Double Cell Box Culvert (1no.)

- Earthworks- Scarification and excavation in cutting sections of existing unsuitable material, filling to Sub-grade with suitable natural gravel materials of 10km

- Pavement Works-Natural Gravel Sub-base and Base Course (150mm thick each) = 10km

- Surfacing Works-Primer Seal and Seal of 10km

        - Physical Progress

ABANDONED: Works suspended and Contractor demobilized from site. Slow rate of progress.

Outstanding works: 11.20km drainage works and 7.5km of Road works.

      - Project Outline - Rehabilitation of Selected Roads in Suhum (10.00km) – Lot 16

        - Project Outline - Lot 16

| Contract Name | Rehabilitation of Selected Roads in Suhum (10.00km) – Lot 16 |
| --- | --- |
| Contractor | Otuboat Limited |
| Municipality/District | Suhum |
| Cumulative Physical Progress (Status) | 47% |
| Financial Progress | 32% |
| Contract Sum | Gh¢8,300,000.00 |
| Revised Contract Sum | Gh¢8,300,000.00 |
| Certified Payments | Gh¢ 2,455,299.48 |
| Funding | Ghana Road Fund |
| Supervising Consultant | Eastern Regional DUR Office |
| Procurement Method | National Competitive Tendering |
| Contract Reference Number | DUR/ER/GRF/PM/REH/2017/018 |
| Contract Award Date | 25th October, 2017 |
| Commencement Date | 22nd December, 2017 |
| Duration | 18 Months |
| Completion Date (As per Contract) | 21st June, 2019 |
| Time Elapsed to Date | 69 Months (383 %) |

        - Scope of Works

The scope of works consists of the upgrading of 5.00km gravel road to bituminous surface. The detailed scope includes the following;

- Construction of 0.6m diameter Open U-drain (7.50km)

- Construction of 0.9m diameter single cell pipe culvert (3 no.)

- Construction of Speed Humps (11 no.)

- Earthworks- Filling to Sub-grade with suitable natural gravel materials of 5.00km

- Pavement Works-Natural Gravel Sub-base & Base Course and Stabilized Base Course (150mm thick each) = 5.00km

- Surfacing Works-Primer Seal and Seal of 5.00km

        - Physical Progress

ABANDONED: Works Suspended and Contractor demobilized from site since August 2021. 2.6km of Primer seal Works Completed. Progress is lagging. Warning letters issued to the Contractor.

### Outstanding works

        - 1km of open drainage works

        - 1nr. 1.2m pipe culvert

        - 9nr. Speed hump

        - 500m of subbase, base and primer seal

        - 5km of seal works

        - Scope of Works

The scope of works consists of the upgrading of 10km gravel road to bituminous surface. The detailed scope includes the following;

- Construction of 0.45m diameter Open U-drain (2.4km)

- Construction of 0.6m diameter Open U-drain (12.55km)

- Construction of 0.9m diameter Open U-drain drains (1.10km)

- Construction of 1.2m Double Cell Pipe Culvert (2no.)

- Construction of 1.2m Single Cell Pipe Culvert (4no.)

- Earthworks- Scarification and excavation in cutting sections of existing unsuitable material, filling to Sub-grade with suitable natural gravel materials of 10km

- Pavement Works-Natural Gravel Sub-base and Base Course (150mm thick each) = 10km

- Surfacing Works-Primer Seal and Seal of 10km

        - Physical Progress

SUBSTANTIALLY COMPLETED: Works Substantially Completed and Partially Taken-Over as of September, 2021. Project is in Defect Liability Period.

      - Project Outline - Rehabilitation of Akim Abomosu Town Roads (2.00km) – Lot 19

        - Project Outline - Lot 19

| Contract Name | Rehabilitation of Akim Abomosu Town Roads (2.00km) – Lot 19 |
| --- | --- |
| Contractor | Doncross Limited |
| Municipality/District | Atiwa West |
| Cumulative Physical Progress (Status) | 98% |
| Financial Progress | 98% |
| Contract Sum | Gh¢2,695,162.67 |
| Revised Contract Sum | Gh¢11,393,918.96 |
| Certified Payments | Gh¢11,239,512.84 |
| Funding | Ghana Road Fund |
| Supervising Consultant | Eastern Regional DUR Office |
| Procurement Method | National Competitive Tendering |
| Contract Reference Number | DUR/ER/GRF/PM/REH/2017/021 |
| Contract Award Date | 25th October, 2017 |
| Commencement Date | 22nd December, 2017 |
| Duration | 30 Months |
| Completion Date (As per Contract) | 21st December, 2018 |
| Revised Completion Date | 20th December, 2020 |
| Time Elapsed to Date | 69 Months (164 %) |

        - Scope of Works (Original)

The scope of works consists of the upgrading of 2.00km gravel road to bituminous surface. The detailed scope includes the following;

- Construction of 0.6m diameter Open U-drain (2.00km)

- Earthworks- Scarification and filling to Sub-grade with suitable natural gravel materials of 2.00km

- Pavement Works-Natural Gravel Sub-base and Base Course (150mm thick each) = 2.00km

- Surfacing Works-Primer Seal and Seal of 2.00km

        - Scope of Works (Additional Works)

The additional works consists of the upgrading of 4.00km gravel road to bituminous surface. The detailed scope includes the following;

- Construction of 0.6m diameter Open U-drain (6.00km)

- Construction of 0.9m diameter Open U-drain (0.25km)

- Construction of trapezoidal drain (0.15km)

- Construction of 0.6m PC (2nr)

- Construction of 0.9m PC (1nr)

- Construction of Reinforced Concrete Wall (150m)

- Construction of Speed Hump (8nr)

- Roads and Paving Works (4.00km)

        - Physical Progress

SUSPENDED: Works Suspended. 5km of primer seal works completed

      - Project Outline - Rehabilitation of Amamprobi By-Pass (3.00km)

– Lot 20

        - Project Outline - Lot 20

| Contract Name | Rehabilitation of Amamprobi By-Pass (3.00km) – Lot 20 |
| --- | --- |
| Contractor | Alaga Limited |
| Municipality/District | Akwapim North |
| Cumulative Physical Progress (Status) | 75% |
| Financial Progress | 93% |
| Contract Sum | Gh¢3,979,961.44 |
| Revised Contract Sum | Gh¢3,979,961.44 |
| Certified Payments | Gh¢3,660,040.05 |
| Funding | Ghana Road Fund |
| Supervising Consultant | Eastern Regional DUR Office |
| Procurement Method | National Competitive Tendering |
| Contract Reference Number | DUR/ER/GRF/PM/REH/2017/022 |
| Contract Award Date | 25th October, 2017 |
| Commencement Date | 22nd December, 2017 |
| Duration | 12 Months |
| Completion Date (As per Contract) | 21st December, 2018 |
| Completion Date (Revised) | 21st June, 2020 |
| Time Elapsed to Date | 69 Months (230 %) |

        - Scope of Works

The scope of works consists of the upgrading of 3km gravel road to bituminous surface. The detailed scope includes the following;

- Construction of 0.6m diameter Open U-drain (2.4km)

- Construction of 0.9m diameter Single Cell Pipe Culvert (2 no.)

- Earthworks- Scarification and excavation in cutting sections of existing unsuitable material, filling to Sub-grade with suitable natural gravel materials of 3km

- Pavement Works-Natural Gravel Sub-base and Base Course (150mm thick each) = 3km

- Surfacing Works-Primer Seal and Seal of 3km

        - Physical Progress

ABANDONED: Works Suspended and Contractor Demobilized from Site. 2.3km of Primer seal works completed 2.5km of 0.6m dia. Concrete U-Drain and 2No. 0.90m dia. Single Cell Pipe Culverts constructed. Additional works being sought through Variation i.e Intersection Improvement of the Mamfe/Koforidua/Amamprobi By - Pass Intersection, Road widening of narrow sections and Construction of the Abiriw Cemetery Road. Overall physical progress is 75%.

Outstanding works: 2.5km of seal works and Intersection improvement works.

      - Project Outline - Construction of Selected Roads in Awukugwa Town Roads (2.50km) - Lot 21

        - Project Outline - Lot 21

| Contract Name | Construction of Selected Roads in Awukugwa Town (2.50km) – Lot 21 |
| --- | --- |
| Contractor | Opanyin Ayeh Construction Limited |
| Municipality/District | Okere |
| Cumulative Physical Progress (Status) | 91% |
| Financial Progress | 85% |
| Contract Sum | Gh¢5,796,528.95 |
| Revised Contract Sum | Gh¢5,796,528.95 |
| Certified Payments | Gh¢3,769,856.09 |
| Funding | Ghana Road Fund |
| Supervising Consultant | Eastern Regional DUR Office |
| Procurement Method | National Competitive Tendering |
| Contract Reference Number | DUR/ER/GRF/PM/CONST/2017/020 |
| Contract Award Date | 25th October, 2017 |
| Commencement Date | 22nd December, 2017 |
| Duration | 12 Months |
| Completion Date (As per Contract) | 21st December, 2018 |
| Completion Date (Revised) | 31st March, 2020 |
| Time Elapsed to Date | 66 Months (238%) |

        - Scope of Works

The scope of works consists of the upgrading of 3km gravel road to bituminous surface. The detailed scope includes the following;

- Construction of 0.45m diameter Open U-drain (0.6km)

- Construction of 0.6m diameter Open U-drain (1.1km)

- Construction of 0.9m diameter Outfall U-drain (190)

- Construction of 0.9m diameter Pipe Culvert (2no.)

- Construction of 1.2m diameter Single Cell Pipe Culvert (1no.)

- Earthworks- Scarification and excavation in cutting sections of existing unsuitable material, filling to Sub-grade with suitable natural gravel materials of 3km

- Pavement Works-Natural Gravel Sub-base and Base Course (150mm thick each) = 3km, Surfacing Works-Primer Seal and Seal of 3km

        - Physical Progress

SUBSTANTIALLY COMPLETED: 2.3km of Drainage and Road works Substantially Completed and Partially Taken-Over as of October, 2021. Project is in Defect Liability Period (DLP).

      - Project Outline - Construction of Abiriw Town Roads (2.00km) –

Lot	22

        - Project Outline - Lot 22

| Contract Name | Construction of Abiriw Town Roads (2.00km) – Lot 22 |
| --- | --- |
| Contractor | Memphis Metropolitan Limited |
| Municipality/District | Okere |
| Cumulative Physical Progress (Status) | 95% |
| Financial Progress | 98% |
| Contract Sum | Gh¢3,491,350.39 |
| Revised Contract Sum | Gh¢7,610,827.69 |
| Certified Payments | Gh¢6,584,768.73 |
| Funding | Ghana Road Fund |
| Supervising Consultant | Eastern Regional DUR Office |
| Procurement Method | National Competitive Tendering |
| Contract Reference Number | DUR/ER/GRF/PM/CONST/2017/024 |
| Contract Award Date | 25th October, 2017 |
| Commencement Date | 22nd December, 2017 |
| Duration | 12 Months |
| Completion Date (As per Contract) | 21st December, 2018 |
| Revised Completion Date | 21st September, 2019 |
| Time Elapsed to Date | 69 Months (329%) |

        - Scope of Works

The scope of works consists of the upgrading of 2km gravel road to bituminous surface. The detailed scope includes the following;

- Construction of 0.6m diameter Open U-drain (2.0km)

- Construction of 0.9m diameter Outfall U-drain (0.1km)

- Earthworks- Scarification and excavation in cutting sections of existing unsuitable material, filling to Sub-grade with suitable natural gravel materials of 2km

- Pavement Works-Natural Gravel Sub-base and Stabilized Base Course (150mm thick each) = 2km

- Surfacing Works-Primer Seal and Seal of 2km

        - Physical Progress

SUBSTANTIALLY COMPLETED: 3km of Drainage and Road Works of Original and Additional Works Substantially Completed and Partially Taken-Over as of September, 2021. Project is in Defect Liability Period (DLP)

      - Project Outline - Construction of Apedwa Town Roads in East Akyem Municipal Area (8.00km) – Lot 26

        - Project Outline - Lot 26

| Contract Name | Construction of Apedwa Town Roads in East Akyem Municipal Area (8.00km) – Lot 26 |
| --- | --- |
| Contractor | Adinani Company Limited |
| Municipality/District | East Akyem |
| Cumulative Physical Progress (Status) | 64% |
| Financial Progress | 48% |
| Contract Sum | Gh¢12,159,059.07 |
| Revised Contract Sum | Gh¢12,159,059.07 |
| Certified Payments | Gh¢ 5,848,495.57 |
| Funding | Ghana Road Fund |
| Supervising Consultant | Eastern Regional DUR Office |
| Procurement Method | National Competitive Tendering |
| Contract Reference Number | DUR/ER/GRF/PM/CONST/2017/028 |
| Contract Award Date | 25th October, 2017 |
| Commencement Date | 22nd December, 2017 |
| Duration | 18 Months |
| Completion Date (As per Contract) | 21st June, 2019 |
| Completion Date (Revised) | 31st March, 2020 |
| Time Elapsed to Date | 69 Months (256 %) |

| Progress Photographs | Plate 1: Spreading of subbase material Plate 2: Compacted base material |
| --- | --- |

### Project Outline - Rehabilitation of Akyem Akropong Town Roads (7.50km) – Lot 28

        - Project Outline - Lot 28

| Contract Name | Rehabilitation of Akyem Akropong Town Roads (7.50km) – Lot 28 |
| --- | --- |
| Contractor | Doncross Limited |
| Municipality/District | Atiwa West |
| Cumulative Physical Progress (Status) | 99% |
| Financial Progress | 99% |
| Contract Sum | Gh¢13,500,000.00 |
| Revised Contract Sum | Gh¢ 38,464,264.06 |
| Certified Payments | Gh¢ 37,178,157.03 |
| Funding | Ghana Road Fund |
| Supervising Consultant | Eastern Regional DUR Office |
| Procurement Method | National Competitive Tendering |
| Contract Reference Number | DUR/ER/GRF/PM/REH/2017/030 |
| Contract Award Date | 25th October, 2017 |
| Commencement Date | 22nd December, 2017 |
| Duration | 18 Months |
| Completion Date (As per Contract) | 21st June, 2019 |
| Revised Completion Date | 31st March, 2023 |
| Time Elapsed to Date | 69 Months (110%) |

### Project Outline - Asphaltic Overlay and Sectional Repair Works on Nana Asafo Adjei – Mile 50 Road (8.70km) – Lot 29

        - Project Outline - Lot 29

| Contract Name | Asphaltic Overlay and Sectional Repair Works on Nana Asafo Adjei – Mile 50 Road (8.70km) – Lot 29 |
| --- | --- |
| Contractor | Justmoh Construction Ltd |
| Municipality/District | New Juaben |
| Cumulative Physical Progress (Status) | 80% |
| Financial Progress | 69% |
| Contract Sum | Gh¢27,447,302.70 |
| Revised Contract Sum | Gh¢43,521,947.48 |
| Certified Payments | Gh¢29,957,623.92 |
| Funding | Ghana Road Fund |
| Supervising Consultant | Eastern Regional DUR Office |
| Procurement Method | National Competitive Tendering |
| Contract Reference Number | DUR/ER/GRF/PM/ASPH./2018/010 |
| Contract Award Date | 28th February, 2018 |
| Commencement Date | 18th April, 2018 |
| Duration | 7 Months |
| Completion Date (As per Contract) | 17th October, 2018 |
| Completion Date (Revised) | 17th April, 2019 |
| Time Elapsed to Date | 63 Months (508 %) |

### Project Outline – Rehabilitation of Begoro Town Roads –

Phase 1 (8.50KM)

        - Project Outline – Lot 30

| Contract Name | Rehabilitation of Begoro Town Roads – Phase 1 (8.50Km) |
| --- | --- |
| Contractor | Western Link Limited |
| Municipality/District | Fanteakwa North |
| Cumulative Physical Progress (Status) | 30% |
| Financial Progress | 21% |
| Contract Sum | Gh¢18,564,150.06 |
| Revised Contract Sum | Gh¢18,564,150.06 |
| Certified Payments | Gh¢ 3,535,984.23 |
| Funding | Ghana Road Fund |
| Supervising Consultant | Eastern Regional DUR Office |
| Procurement Method | National Competitive Tendering |
| Contract Reference Number | DUR/ER/GRF/PM/CONST./2018/003 |
| Contract Award Date | 29th October, 2018 |
| Commencement Date | 26th February, 2019 |
| Duration | 12 Months |
| Completion Date (As per Contract) | 25th February, 2020 |
| Completion Date (Revised) | 25th December, 2021 |
| Time Elapsed to Date | 55 Months (250%) |

### Rehabilitation of Begoro Town Roads – Phase 2 (7.00KM)

        - Project Outline

| Contract Name | Rehabilitation of Begoro Town Roads – Phase 2 (7.00Km) |
| --- | --- |
| Contractor | Aya Ltd |
| Municipality/District | Fanteakwa North |
| Cumulative Physical Progress (Status) | 45% |
| Financial Progress | 38% |
| Contract Sum | Gh¢15,301,250.97 |
| Revised Contract Sum | Gh¢15,301,250.97 |
| Certified Payments | Gh¢5,347,533.55 |
| Funding | Ghana Road Fund |
| Supervising Consultant | Eastern Regional DUR Office |
| Procurement Method | National Competitive Tendering |
| Contract Reference Number | DUR/ER/GRF/PM/CONST./2018/004 |
| Contract Award Date | 29th October, 2018 |
| Commencement Date | 26th February, 2019 |
| Duration | 12 Months |
| Completion Date (As per Contract) | 25th February, 2020 |
| Completion Date (Revised) | 23rd February, 2024 |
| Time Elapsed to Date | 54 Months (92%) |

### Project Outline – Rehabilitation of Begoro Town Roads –

Phase 3 (1.50KM)

        - Project Outline

| Contract Name | Rehabilitation of Begoro Town Roads – Phase 3 (1.50Km) |
| --- | --- |
| Contractor | K.B.A. Engineers Limited |
| Municipality/District | Fanteakwa North |
| Cumulative Physical Progress (Status) | 25% |
| Financial Progress | 15% |
| Contract Sum | Gh¢4,833,052.32 |
| Revised Contract Sum | Gh¢4,833,052.32 |
| Certified Payments | Gh¢650,639.05 |
| Funding | Ghana Road Fund |
| Supervising Consultant | Eastern Regional DUR Office |
| Procurement Method | National Competitive Tendering |
| Contract Reference Number | DUR/ER/GRF/PM/CONST./2018/005 |
| Contract Award Date | 29th October, 2018 |
| Commencement Date | 26th February, 2019 |
| Duration | 12 Months |
| Completion Date (As per Contract) | 25th February, 2020 |
| Time Elapsed to Date | 55 Months (458%) |

### Project Outline – Rehabilitation of Bedtime Hotel/Abotanso

/Sempoa Miensa Area Roads (5.0KM)

        - Project Outline

| Contract Name | Rehabilitation of Bedtime Hotel/Abotanso/Sempoa Miensa Area Roads (5.0Km) |
| --- | --- |
| Contractor | Mohajara Ventures |
| Municipality/District | New Juaben South |
| Cumulative Physical Progress (Status) | 42% |
| Financial Progress | 43% |
| Contract Sum | Gh¢16,513,119.22 |
| Revised Contract Sum | Gh¢16,513,119.22 |
| Certified Payments | Gh¢ 7,239,010.92 |
| Funding | Ghana Road Fund |
| Supervising Consultant | Eastern Regional DUR Office |
| Procurement Method | National Competitive Tendering |
| Contract Reference Number | DUR/ER/GRF/PM/REH./2018/LOT01 |
| Contract Award Date | 17th February, 2018 |
| Commencement Date | 2nd November, 2018 |
| Duration | 12 Months |
| Completion Date (As per Contract) | 1st November, 2019 |
| Completion Date (Revised) | 9th December, 2022 |
| Time Elapsed to Date | 58 Months (118%) |

### Project Outline – Construction of Selected Roads around Daasebre Dwamena Area (1.50km)

        - Project Outline

| Contract Name | Construction of Selected Roads around Daasebre Dwamena Area (1.50Km) |
| --- | --- |
| Contractor | Navacon Company Limited |
| Municipality/District | New Juaben South |
| Cumulative Physical Progress (Status) | 85% |
| Financial Progress | 42% |
| Contract Sum | Gh¢5,176,502.98 |
| Revised Contract Sum | Gh¢5,176,502.98 |
| Certified Payments | Gh¢ 1,942,448.19 |
| Funding | Ghana Road Fund |
| Supervising Consultant | Eastern Regional DUR Office |
| Procurement Method | National Competitive Tendering |
| Contract Reference Number | DUR/ER/GRF/PM/CONST./2018/003 |
| Contract Award Date | 29th October, 2018 |
| Commencement Date | 16th January, 2019 |
| Duration | 12 Months |
| Completion Date (As per Contract) | 15th January, 2020 |
| Completion Date (Revised) | 14th September, 2021 |
| Time Elapsed to Date | 58 Months (175%) |

### Project Outline – Rehabilitation of Adweso, Abugri and Old Estate Roads in Koforidua (5.00km) – Lot 1

        - Project Outline

| Contract Name | Rehabilitation of Adweso, Abugri and Old Estate Roads in Koforidua (5.00km) |
| --- | --- |
| Contractor | Thames Construction Limited |
| Municipality/District | New Juaben South |
| Cumulative Physical Progress (Status) | 40% |
| Financial Progress | 33% |
| Contract Sum | Gh¢15,422,204.20 |
| Revised Contract Sum | Gh¢15,422,204.20 |
| Certified Payments | Gh¢ 4,628,385.05 |
| Funding | Ghana Road Fund |
| Supervising Consultant | Eastern Regional DUR Office |
| Procurement Method | National Competitive Tendering |
| Contract Reference Number | - |
| Contract Award Date | 29th October, 2018 |
| Commencement Date | 8th November, 2019 |
| Duration | 12 Months |
| Completion Date (As per Contract) | 7th November, 2020 |
| Time Elapsed to Date | 46 Months (383%) |

### Project Outline – Asphaltic Overlay on Selected Roads in Suhum (10.00km) -Lot 4

        - Project Outline

| Contract Name | Asphaltic Overlay on Selected Roads in Suhum (10.00km) |
| --- | --- |
| Contractor | Justmoh Construction Limited |
| Municipality/District | Suhum |
| Cumulative Physical Progress (Status) | 89% |
| Financial Progress | 90% |
| Contract Sum | Gh¢20,415,283.10 |
| Revised Contract Sum | Gh¢90,161,919.79 |
| Certified Payments | Gh¢ 80,503,770.90 |
| Funding | Ghana Road Fund |
| Supervising Consultant | Eastern Regional DUR Office |
| Procurement Method | National Competitive Tendering |
| Contract Reference Number | DUR/ER/GRF/PM/ASPHALT/SUHUM/2019/LOT01 |
| Contract Award Date | 11th June, 2019 |
| Commencement Date | 8th November, 2019 |
| Duration | 6 Months |
| Completion Date (As per Contract) | 7th May, 2020 |
| Revised Completion Date | 6th August, 2023 |
| Time Elapsed to Date | 58 Months (102%) |

### Project Outline - Sectional Construction of Suhyen-Akwadum Road in New Juaben North Municipality (10.00km) - Lot 1

        - Project Outline

| Contract Name | Sectional Construction of Suhyen - Akwadum Road in New Juaben North Municipality (10.00km) |
| --- | --- |
| Contractor | Altep Limited |
| Municipality/District | New Juaben North |
| Cumulative Physical Progress (Status) | 18% |
| Financial Progress | 15% |
| Contract Sum | Gh¢25,315,139.68 |
| Revised Contract Sum | Gh¢25,315,139.68 |
| Certified Payments | Gh¢ 4,223,987.98 |
| Funding | Ghana Road Fund |
| Supervising Consultant | Eastern Regional DUR Office |
| Procurement Method | National Competitive Tendering |
| Contract Reference Number | - |
| Contract Award Date | 11th June, 2019 |
| Commencement Date | 5th December, 2019 |
| Duration | 18 Months |
| Completion Date (As per Contract) | 4th June, 2021 |
| Time Elapsed to Date | 45 Months (250%) |

### Project Outline - Construction of Ayisi Okyere Road and Links

– Peduase (4.78km) - Lot 1

        - Project Outline

| Contract Name | Construction of Ayisi Okyere Road and Links– Peduase (4.78km) |
| --- | --- |
| Contractor | First Sky Limited |
| Municipality/District | Akuapem North |
| Cumulative Physical Progress (Status) | 23% |
| Financial Progress | 23% |
| Contract Sum | Gh¢28,725,919.96 |
| Revised Contract Sum | Gh¢28,725,919.96 |
| Certified Payments | Gh¢ 6,022,736.16 |
| Funding | Ghana Road Fund |
| Supervising Consultant | Eastern Regional DUR Office |
| Procurement Method | National Competitive Tendering |
| Contract Reference Number | DUR/ER/GRF/PM/PEDUASE/CONST/2019/002 |
| Contract Award Date | 1st November, 2019 |
| Commencement Date | 24TH January, 2020 |
| Duration | 12 Months |
| Completion Date (As per Contract) | 23rd January, 2021 |
| Time Elapsed to Date | 44 Months (367%) |

### Project Outline -	Rehabilitation of Selected Roads in Atekyem, Koforidua (8.00km) - Lot 2

        - Project Outline

| Contract Name | Rehabilitation of Selected Roads in Atekyem, Koforidua (8.00km) |
| --- | --- |
| Contractor | Kingdwosco Enterprise Limited |
| Municipality/District | New Juaben South |
| Cumulative Physical Progress (Status) | 66% |
| Financial Progress | 78% |
| Contract Sum | Gh¢20,738,682.93 |
| Revised Contract Sum | Gh¢77,044,393.73 |
| Certified Payments | Gh¢ 55,971,806.86 |
| Funding | Ghana Road Fund |
| Supervising Consultant | Eastern Regional DUR Office |
| Procurement Method | National Competitive Tendering |
| Contract Reference Number | DUR/ER/GRF/PM/REHAB/ATEKYEM KOF./2019/003 |
| Contract Award Date | 1st November, 2019 |
| Commencement Date | 20th November, 2019 |
| Duration | 18 Months |
| Completion Date (As per Contract) | 19th May, 2021 |
| Revised Completion Date | 18th May, 2022 |
| Time Elapsed to Date | 46 Months (153%) |

### Project Outline -	Rehabilitation of Selected Roads around Koforidua Technical University (3.50km) - Lot 3

        - Project Outline

| Contract Name | Rehabilitation of Selected Roads around Koforidua Technical University (3.50km) |
| --- | --- |
| Contractor | G & S Construction Company Limited |
| Municipality/District | New Juaben South |
| Cumulative Physical Progress (Status) | 20% |
| Financial Progress | 20% |
| Contract Sum | Gh¢11,366,181.08 |
| Revised Contract Sum | Gh¢11,366,181.08 |
| Certified Payments | Gh¢ 2,075,596.08 |
| Funding | Ghana Road Fund |
| Supervising Consultant | Eastern Regional DUR Office |
| Procurement Method | National Competitive Tendering |
| Contract Reference Number | DUR/GR/GRF/PM/REHAB/KOFORIDUA/2019/004 |
| Contract Award Date | 1st November, 2019 |
| Commencement Date | 14th January 2020 |
| Duration | 12 Months |
| Completion Date (As per Contract) | 13th January, 2021 |
| Time Elapsed to Date | 44 Months (367%) |

### Project Outline -	Construction of Presbyterian Lay Training School Centre Road (2.10km), Odumasi Krobo - Lot 1

        - Project Outline

| Contract Name | Construction of Presbyterian Lay Training School Centre Road (2.10km), Odumasi Krobo |
| --- | --- |
| Contractor | Memphis Metropolitan Limited |
| Municipality/District | Lower Manya Krobo |
| Cumulative Physical Progress (Status) | 33% |
| Financial Progress | 33% |
| Contract Sum | Gh¢7,224,255.80 |
| Revised Contract Sum | Gh¢ 13,834,929.52 |
| Certified Payments | Gh¢ 4,157,323.29 |
| Funding | Ghana Road Fund |
| Supervising Consultant | Eastern Regional DUR Office |
| Procurement Method | National Competitive Tendering |
| Contract Reference Number | DUR/ER/GRF/PM/ODUMASE KROBO/CONST./2019/001 |
| Contract Award Date | 4th November, 2019 |
| Commencement Date | 13th May, 2020 |
| Duration | 12 Months |
| Duration (Revised) | 18 Months |
| Completion Date (As per Contract) | 12th May, 2021 |
| Completion Date (Revised) | 5th December, 2021 |
| Time Elapsed to Date | 45 Months (184%) |

### Project Outline -	Upgrading of Asesewa Town Roads Phase 1 (4.90km) - Lot 2

        - Project Outline

| Contract Name | Upgrading of Asesewa Town Roads Phase 1 (4.90km) |
| --- | --- |
| Contractor | Opanyin Ayeh Construction Limited |
| Municipality/District | Upper Manya Krobo |
| Cumulative Physical Progress (Status) | 66% |
| Financial Progress | 52% |
| Contract Sum | Gh¢11,010,994.80 |
| Revised Contract Sum | Gh¢11,010,994.80 |
| Certified Payments | Gh¢6,714,980.76 |
| Funding | Ghana Road Fund |
| Supervising Consultant | Eastern Regional DUR Office |
| Procurement Method | National Competitive Tendering |
| Contract Reference Number | DUR/ER/GRF/PM/ASESEWA/UPGRADING/2019/002 |
| Contract Award Date | 1st November, 2019 |
| Commencement Date | 14th May, 2020 |
| Duration | 18 Months |
| Completion Date (As per Contract) | 13th November, 2021 |
| Time Elapsed to Date | 40 Months (222%) |

### Project Outline -	Rehabilitation of Akim Oda Senior High School Roads (Odasco), Akim Oda (3.00km) - Lot 3

        - Project Outline

| Contract Name | Rehabilitation of Akim Oda Senior High School Roads (Odasco), Akim Oda (3.00km) |
| --- | --- |
| Contractor | Kasmo Company Limited |
| Municipality/District | Birim Central |
| Cumulative Physical Progress (Status) | 10% |
| Financial Progress | 11% |
| Contract Sum | Gh¢8,550,674.80 |
| Revised Contract Sum | Gh¢8,550,674.80 |
| Certified Payments | Gh¢ 849,161.41 |
| Funding | Ghana Road Fund |
| Supervising Consultant | Eastern Regional DUR Office |
| Procurement Method | National Competitive Tendering |
| Contract Reference Number | DUR/ER/GRF/PM/AKIM ODA/REH./2019/002 |
| Contract Award Date | 4th November, 2019 |
| Commencement Date | 14th March, 2020 |
| Duration | 12 Months |
| Completion Date (As per Contract) | 13th March, 2021 |
| Time Elapsed to Date | 42 Months (350%) |

### Project Outline -	Rehabilitation of Asamankese Town Roads (15.00km) – Lot 1

        - Project Outline

| Contract Name | Rehabilitation of Asamankese Town Roads (15.00km) |
| --- | --- |
| Contractor | Hardwick |
| Municipality/District | West Akim |
| Cumulative Physical Progress (Status) | 10% |
| Financial Progress | 11% |
| Contract Sum | Gh¢58,136,691.04 |
| Revised Contract Sum | Gh¢58,136,691.04 |
| Certified Payments | Gh¢ 6,478,483.25 |
| Funding | Ghana Road Fund |
| Supervising Consultant | Eastern Regional DUR Office |
| Procurement Method | National Competitive Tendering |
| Contract Reference Number | DUR/ER/GRF/PM/ASAMANKESE/REH./2019/005 |
| Contract Award Date | 1st November, 2019 |
| Commencement Date | 25th March, 2020 |
| Duration | 24 Months |
| Completion Date (As per Contract) | 24th March, 2022 |
| Time Elapsed to Date | 42 Months (175%) |

### Project Outline - Asphaltic Overlay on Apedwa – Kyebi – Bunso (Apedwa Junction to Kyebi Akwadum) (0+000 – 10+500) – Lot 1

        - Project Outline

| Contract Name | Asphaltic Overlay on Apedwa – Kyebi – Bunso (Apedwa Junction to Kyebi Akwadum) – Lot 1 |
| --- | --- |
| Contractor | Ussuya (Ghana) Limited |
| Municipality/District | East Akim |
| Cumulative Physical Progress (Status) | 92% |
| Financial Progress | 98% |
| Contract Sum | Gh¢32,011,601.56 |
| Revised Contract Sum | - |
| Certified Payments | Gh¢ 31,918,916.30 |
| Funding | Ghana Road Fund |
| Supervising Consultant | Eastern Regional DUR Office |
| Procurement Method | National Competitive Tendering |
| Contract Reference Number | DUR/ER/GRF/APEDWA-KYEBI-AKWADUM/ASPH./2020/001 |
| Contract Award Date | 27th May, 2020 |
| Commencement Date | 7th July, 2020 |
| Duration | 12 Months |
| Completion Date (As per Contract) | 6th July, 2021 |
| Time Elapsed to Date | 38 months (317%) |

### Project Outline - Asphaltic Overlay on Apedwa – Kyebi – Bunso (Sagyemase - Bunso Junction) (21+000 – 31+500) – Lot 2

        - Project Outline

| Contract Name | Asphaltic Overlay on Apedwa – Kyebi – Bunso (Apedwa Junction to Kyebi Akwadum) – Lot 1 |
| --- | --- |
| Contractor | Hardwick Limited |
| Municipality/District | East Akim |
| Cumulative Physical Progress (Status) | 95% |
| Financial Progress | 135% |
| Contract Sum | Gh¢30,832,141.90 |
| Revised Contract Sum | Gh¢130,615,741.90 |
| Certified Payments | Gh¢ 176,653,914.94 |
| Funding | Ghana Road Fund |
| Supervising Consultant | Eastern Regional DUR Office |
| Procurement Method | National Competitive Tendering |
| Contract Reference Number | DUR/ER/GRF/APEDWA-KYEBI-BUNSO/ASPH./2020/002 |
| Contract Award Date | 27th May, 2020 |
| Commencement Date | 7th July, 2020 |
| Duration | 12 Months |
| Completion Date (As per Contract) | 6th July, 2021 |
| Duration (Revised) | 42 Months |
| Completion Date (Revised) | 2nd December, 2023 |
| Time Elapsed to Date | 38 months (90%) |

### Project Outline - Rehabilitation of Asamang Tamfoe Town Roads in Atiwa East District – Eastern Region (8.50km) – Lot 1

        - Project Outline

| Contract Name | Rehabilitation of Asamang Tamfoe Town Roads in Atiwa East District – Eastern Region (8.50km) – Lot 1 |
| --- | --- |
| Contractor | Kingdwosco Enterprises Limited |
| Municipality/District | Atiwa East |
| Cumulative Physical Progress (Status) | 45% |
| Financial Progress | 22% |
| Contract Sum | Gh¢38,468,821.20 |
| Revised Contract Sum | Gh¢ 85,799,933.20 |
| Certified Payments | Gh¢18,968,363.39 |
| Funding | Ghana Road Fund |
| Supervising Consultant | Eastern Regional DUR Office |
| Procurement Method | National Competitive Tendering |
| Contract Reference Number | DUR/ER/GRF/PM/ASAMANG TAMFOE/REHAB./2020/001 |
| Contract Award Date | 27th May, 2020 |
| Commencement Date | 2nd September, 2020 |
| Duration | 18 Months |
| Completion Date (As per Contract) | 1st March, 2022 |
| Duration (Revised) | 42 months |
| Revised Completion Date | 27th February, 2024 |
| Time Elapsed to Date | 36 months (86%) |

### Project Outline -	Construction of Kofi Pare Road and Anum Apapam Town Roads in Ayensuano District PH 1 – Lot 1

        - Project Outline

| Contract Name | Construction of Kofi Pare Road and Anum Apapam Town Roads in Ayensuano District Phase 1 (5.00km) - Lot 1 |
| --- | --- |
| Contractor | Akumasa Company Limited |
| Municipality/District | Ayensuano District |
| Cumulative Physical Progress (Status) | 2% |
| Financial Progress | - |
| Contract Sum | Gh¢19,361,885.90 |
| Revised Contract Sum | Gh¢19,361,885.90 |
| Certified Payments | - |
| Funding | Ghana Road Fund |
| Supervising Consultant | Eastern Regional DUR Office |
| Procurement Method | National Competitive Tendering |
| Contract Reference Number | - |
| Contract Award Date | 10th September, 2020 |
| Commencement Date | 26th November, 2020 |
| Duration | 12 Months |
| Completion Date (As per Contract) | 25th November, 2021 |
| Revised Completion Date | - |
| Time Elapsed to Date | 34 months (283%) |

### Project Outline - Partial Reconstruction of Sunrise FM, St. Joseph Hospital, Pope Johns SHS and Prisons Roads, Koforidua (5.00km)

        - Project Outline

| Contract Name | Partial Reconstruction of Sunrise FM, St. Joseph Hospital, Pope Johns SHS and Prisons Roads, Koforidua (5.00km) |
| --- | --- |
| Contractor | China Jiangxi Engineering Limited |
| Municipality/District | New Juaben North |
| Cumulative Physical Progress (Status) | 10% |
| Financial Progress | 8% |
| Contract Sum | Gh¢16,964,760.51 |
| Revised Contract Sum | Gh¢16,964,760.51 |
| Certified Payments | Gh¢ 1,216,476.90 |
| Funding | Ghana Road Fund |
| Supervising Consultant | Eastern Regional DUR Office |
| Procurement Method | National Competitive Tendering |
| Contract Reference Number | DUR/ER/GRF/PM/KOFORIDUA/PARTIAL RECONST./2020/001 |
| Contract Award Date | 19th October, 2020 |
| Commencement Date | 20th September, 2021 |
| Duration | 12 Months |
| Completion Date (As per Contract) | 19th September, 2022 |
| Revised Completion Date | 19th September, 2022 |
| Time Elapsed to Date | 21 Months (200%) |

### Project Outline - Rehabilitation of Akropong school for the blind and selected town roads in Akuapem North Municipality (7.50km) – PH 1

        - Project Outline

| Contract Name | Rehabilitation of Akropong school for the blind and selected town roads in Akuapem North Municipality (7.50km)- PH 1 |
| --- | --- |
| Contractor | Facol Limited |
| Municipality/District | Akuapem North |
| Cumulative Physical Progress (Status) | 25% |
| Financial Progress | 9% |
| Contract Sum | Gh¢ 24,241,052.66 |
| Revised Contract Sum | Gh¢ 24,241,052.66 |
| Certified Payments | Gh¢ 2,360,555.94 |
| Funding | Ghana Road Fund |
| Supervising Consultant | Eastern Regional DUR Office |
| Procurement Method | National Competitive Tendering |
| Contract Reference Number | - |
| Contract Award Date | 25th September, 2020 |
| Commencement Date | 26th November, 2020 |
| Duration | 18 Months |
| Completion Date (As per Contract) | 25th May, 2022 |
| Time Elapsed to Date | 158 Months (189%) |

### Project Outline -	Construction of Selected Roads in Akyem Asamama and Bomaa in Atiwa West District (8.00km)

        - Project Outline

| Contract Name | Construction of Selected Roads in Akyem Asamama and Bomaa in Atiwa West District (8.00km) |
| --- | --- |
| Contractor | Doncross Limited |
| Municipality/District | Atiwa West |
| Cumulative Physical Progress (Status) | 96% |
| Financial Progress | 78% |
| Contract Sum | Gh¢ 32,176,531.90 |
| Revised Contract Sum | - |
| Certified Payments | Gh¢ 23,695,322.84 |
| Funding | Ghana Road Fund |
| Supervising Consultant | Eastern Regional DUR Office |
| Procurement Method | Single Sourcing |
| Contract Reference Number | DUR/ER/GRF/CONST./ER/HO/2022/01 |
| Contract Award Date | 31st May, 2022 |
| Commencement Date | 31st August, 2022 |
| Duration | 24 Months |
| Completion Date (As per Contract) | 30th August, 2024 |
| Time Elapsed to Date | 12 Months (50%) |

### Cocoa Roads Rehabilitation Programme

The Cocoa Roads Development Project is a road rehabilitation programme in cocoa-growing areas in the country being funded by the Ghana Cocoa Board (COCOBOD) with key objective of facilitating the carting of foodstuff from farming communities to marketing centers. It was also intended to boost cocoa production through reduction in post-harvest losses thereby promoting socio-economic development.

Altogether, two (2) contracts consisting of one (1) within West Akim Municipality and one (1) in Kwaebibrim District were being supervised by Eastern Regional Office of Department of Urban Roads on behalf of Ministry of Roads and Highways and Department of Urban Roads which are the implementing Agencies. However, 1no. Contract has been terminated due to non-performance. The contracts are listed below;

- Construction of selected Roads in Asamankese (5km) – (Terminated)

- Partial Reconstruction of Kade Town Roads (5km) – (Substantially Completed)

  - Project Outline

| Contract Name | Partial Reconstruction of Kade Town Roads (5.00km) |
| --- | --- |
| Contractor | Myturn Limited |
| Municipality/District | Kade |
| Cumulative Physical Progress (Status) | 98% |
| Financial Progress | 98% |
| Contract Sum | Gh¢8,592,830.11 |
| Revised Contract Sum | Gh¢8,592,830.11 |
| Certified Payments | Gh¢ 10,515,475.28 |
| Funding | COCOBOD |
| Supervising Consultant | Eastern Regional DUR Office |
| Procurement Method | Restricted Tendering |
| Contract Reference Number | - |
| Contract Award Date | 13th July, 2015 |
| Commencement Date | 31st March, 2016 |
| Duration | 18 Months |
| Completion Date (As per Contract) | 30th March, 2017 |
| Revised Completion Date | - |
| Time Elapsed to Date | 96 Months (800%) |

### Consultancy Services

Knights Ghana Limited, acting through the Government of Ghana (MRH), is undertaking the design, fabrication, supply, and installation of 50 no. Czech Modular Steel Bridges and related civil works in Ghana. The Eastern region has benefited from this initiative, resulting in the construction of 2 no. Czech modular steel bridges in Asokore Kuma (New Juaben North) and Kyebi (Abuakwa South).

The regional office is providing supervisory support to the project. Despite the recent suspension of works, progress achieved is at a substantial stage. The details of the project are presented in Table 4. 1 and Table 4. 2.

Table 4. 1: Construction of Composite Bridges at Asokore-Kuma

| Contract Name | Construction of Fifty (50) No. Composite Bridges at Various Locations in Ghana (Lot 1-16 Bridges) – Bridge No. Lot 1/04/04 Located on Asokore-Kuma Road |
| --- | --- |
| Contractor | Kehentson Company Limited |
| Municipality/District | New Juaben North |
| Physical Progress | 58% |
| Financial Progress | 57% |
| Contract Sum | Gh¢ 3,739,539.96 |
| Certified Payments | Gh¢ 2,119,272.49 |
| Funding | Knights Ghana Limited |
| Supervising Consultant | Eastern Regional DUR Office |
| Contract Award Date | 2nd February, 2021 |
| Commencement Date | 10th April, 2021 |
| Duration | 9 Months |
| Completion Date (As per Contract) | 9th January, 2022 |
| Time Elapsed to Date | 29 Months (322%) |
| Remarks | Contractor has suspended works and demobilized from site. |

Construction of Composite Bridges at Kyebi

| Contract Name | Construction of Fifty (50) No. Composite Bridges at Various Locations in Ghana– Bridge Located on Zongo-Kassadjan Road |
| --- | --- |
| Contractor | Broad Consult |
| Municipality/District | Abuakwa South |
| Physical Progress | 60% |
| Financial Progress | - |
| Contract Sum | Gh¢ 4,229,630.00 |
| Certified Payments | - |
| Funding | Knights Ghana Limited |
| Supervising Consultant | Eastern Regional DUR Office |
| Contract Award Date | 12th April, 2021 |
| Commencement Date | 26th April, 2021 |
| Duration | 9 Months |
| Completion Date (As per Contract) | 12th January, 2022 |
| Time Elapsed to Date | 29 Months (322%) |
| Remarks | Contractor has suspended works and demobilized from site. |